## Project Schedule
JobIntel Platform | [16 empty] | Project Schedule
Start Week | Oct 5, 2025
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | Notes
Starting | Oct 05 | Oct 12 | Oct 19 | Oct 26 | Nov 02 | Nov 09 | Nov 16 | Nov 23 | Nov 30 | Dec 07 | Dec 14 | Dec 21 | Dec 28 | Jan 04 | Jan 11 | Jan 18 | Jan 25 | Feb 01 | Feb 08 | Feb 15 | Feb 22 | Mar 01 | Mar 08 | Mar 15 | Mar 22 | Mar 29 | Apr 05 | Apr 12 | Apr 19 | Apr 26 | May 03 | May 10 | May 17 | May 24 | May 31 | Jun 07
Phase One Research | Topic Research & Selection | [35 empty] | P
|  | Business Requirements | [34 empty] | R
|  | Tools Installation | [34 empty] | O
|  |  | Technology Study | [33 empty] | J
Phase Two Analysis & Design | [6 empty] | Use Case Analysis | [29 empty] | E
[7 empty] | Use Case Scenarios | [29 empty] | C
[7 empty] | DFD | [29 empty] | T
UI Wireframes (Figma)
[7 empty] | Sequence Diagrams | [29 empty] | E
[9 empty] | ERD Design | [27 empty] | N
[11 empty] | Database Schema | [25 empty] | D
Class Diagrams
Phase Three Implementation | [11 empty] | Frontend Implementation
Backend Setup & Database
API Development
AI Model Development
AI API Integration
Phase Four Testing | [30 empty] | Frontend Testing
Backend Testing
AI Testing
Integration Testing
Phase Five Documentation | [12 empty] | Technical Documentation
Final Report
Presentation Preparation